# OneDrive Migration Playbook: Serco Commercial to Serco GCCH

## Migration Participants

| Team | Members | Notes |
| --- | --- | --- |
| Migration Team | NonEXO: Chris Burns, (602) 335-9095 (PM) Amy Kimball, (602) 402-6631 |  |
| Serco | Rick Rosello, (631) 565-2397 Kip Jackson, (571) 279-5955 (PM) Anthony Wilson, (646) 477-2226 |  |
| Communications | Serco Comms Team |  |

## Migration Wave Overview

- 2-week Wave

  - 2 weeks prior to Friday night cutover: Laptops are shipped with 1st comm

  - 2 weeks prior to Friday night cutover: Sync job begin

  - 5 days prior to Friday night cutover: UAT Starts

  - Day of Friday night cutover: UAT Ends at 12pm EST

  - Cutover over Friday starts at 6pm EST

  - Cutover ends no later than Monday morning 6am EST

  - Hypercare runs Monday-Friday following cutover

## Migration Wave Details

### INITIAL COMMUNICATION: 2 WEEKS BEFORE CUTOVER WEEKEND

Purpose: Bring awareness to End Users in Wave

- Send email (“It’s Coming”) to all Users – Serco Comms Team

  - Users will receive their laptops and credentials 2 weeks prior to cutover weekend

  - Users will have been working in both environments.

IT PREPARATION TASKS: BEFORE CUTOVER WEEKEND

Purpose: Preparation tasks to be completed by the IT Team(s) before customer engagement.

- Migration Team notifies Rick that syncing starts Monday and CR can be initiated.

- Anthony to verify final list of Users to sync.

- Migration Team validates Users exist on Target tenant & that users are assigned M365 license.

- Migration Team Users’ OneDrive provisioned in Target Tenant.

INITIATE: 2 WEEKS PRIOR TO CUTOVER WEEKEND

Purpose: Syncing of data begins

- Serco Comms Team sends email (“UAT is coming”)

- Migration Team kicks off sync job

The Migration Team schedules/executes migration jobs, monitors progress, review logs and checks for defects or errors, troubleshoots, and re-run jobs as needed.

Keep in mind:

- Quest What Migrates and What Does Not: https://support.quest.com/technical-documents/on-demand-migration/current/user-guide/13#TOPIC-2147816

UAT: 1 WEEK PRIOR TO CUTOVER WEEKEND

Purpose: User validation of sync job

- Serco Comms Team sends email (“UAT is here”)

### VELOCITY: FRIDAY OF CUTOVER WEEKEND

Purpose: Cutover

- Migration Activities

- Morning:

  - Serco Comms Team sends “It’s Here” email to affected users notifying them of the migration & also asking them to close out all files

- Evening/ Early next morning

  - Perform Nightly Migrations – done by Migration Team

- Check Migration Job configurations

- Schedule Migration Jobs to start after 6pm EST

- Review logs and check for defects or errors after the Migration Job is completed.

- Fix defects / errors / issues if any

### VELOCITY: FRIDAY OF CUTOVER WEEKEND

Purpose: Cutover Complete

Sunday night or Monday early morning:

- Migration Team sends Completion Email + links to Reports to PM & interested parties. Call out Exceptions / Issues

- Serco Comms Team sends out “It’s Done” email. For users with Exceptions, send “Exceptions Found” email

- Migration Team sends Robert a script to put OneDrive into Read-Only.

  - Be sure to remove any people in the “DO NOT CUTOVER” list from the script.

### HYPERCARE: DURATION IS FOR 1-WEEK AFTER THE MIGRATION

Purpose: Provide support for the just-completed Migration

- Hypercare period. Migration Team to address any questions / issues on the just completed migration, as necessary.

### IT CLOSE OUT TASKS: DURATION IS FOR 1-WEEK AFTER THE MIGRATION

Purpose: Complete close-out tasks

- Tell Rick that he may close out CRs

- Remove Migrations accounts access from the Source & Target OneDrive site collections.