## Sheet2
Corp Services
Citizen Services
Agile+
Homegrown,SaaS, Web Accesible

## Executive Brief
Theme | Executive Summary | Business Impact | Root Cause Type | Risk if Unaddressed | Recommended Focus Area
Cross-Tenant Communication & Collaboration | Users experience persistent friction communicating between Commercial and GCC High tenants, particularly via email, Outlook, and Teams. | Missed communications, stalled meetings, reduced productivity during migration period. | Policy / Tooling | Continued operational inefficiency and loss of confidence in GCC High environment. | Clarify supported cross-tenant behaviors and harden tooling consistency.
M365 Data & Workload Migration Gaps | Critical user data and collaboration artifacts did not consistently migrate from Commercial to GCC High. | Loss of access to files, Teams chats/channels, calendars, and institutional knowledge. | Migration | Business continuity risk and manual workarounds becoming permanent. | Define authoritative migration scope and remediation paths.
Application Availbility & Readiness

## Issue Register
Issue ID | Issue Title | Description | Category | Systems Impacted | User Impact
ISS-01 | Email forwarding and delivery inconsistencies | Commercial emails are not appearing in GCC High; users unclear on forwarding requirements. | Policy | Exchange Online | High
ISS-02 | Teams meeting integration missing in Outlook | Teams add-in missing or removed post-migration, blocking virtual meeting scheduling. | Tooling | Outlook, Teams | High
ISS-03 | SharePoint/Teams data not fully migrated | Data appears partially migrated from Commercial tenant. | Migration | SharePoint | High
ISS-04 | Users unclear on GCC High vs Commercial usage model | Users unsure which tasks must remain on Commercial vs GCC High environments. | Training | End User Workflow | Medium
ISS-05 | Download, Print, Sync in GCCH unaviable | Users cannot download files are templates from (read-only) SharePoint or Teams repositorys, impacting operations and deliverables | Policy | M36 Suite | High

## Heatmap Analysis
Issue Title | Frequency | Resolution State | Primary Failure Mode | Heat Indicator
Email forwarding and delivery inconsistencies | High | Partially Resolved / Workaround | Policy Constraint | 🔴 High
Teams meeting integration missing in Outlook | High | Mixed | Tooling Gap | 🔴 High
OneDrive and SharePoint data not fully migrated | Medium | Mixed | Migration Gap | 🟠 Medium

## IT Backlog
Backlog Item | Linked Issues | Category | Proposed Owner | Effort | Business Value | Priority | Notes
Define and publish cross-tenant email and meeting behavior | ISS-01 | Policy | Security / Messaging | M | Reduces communication failures | High | Include sensitivity labels and forwarding guidance
Stabilize Teams-Outlook integration in GCC High | ISS-02 | Tooling | M365 Platform | M | Restores meeting productivity | High | Validate add-in persistence post-update
Remediate incomplete OneDrive/SharePoint migrations | ISS-03 | Migration | Migration Team | L | Prevents data loss | High | Include H: drive and legacy sources

## INC Report 04.06.26
Task | State | Created by | Short description | Description | Assigned to | Created | Active | Work notes | Comments and Work notes | Business elapsed time | Business pause duration | Business elapsed percentage | Business time left | Actual elapsed time | Stop time | Has breached | Original breach time | Pause duration | Assignment group | Tags | Number
INC0624420 | New | Michael.Lee@serco-na.com | Add access to serco-na.com environment through remote desktop on gcc-h to allow more efficient access to network while we have to work in multiple environments. | Add access to serco-na.com environment through remote desktop on gcc-h to allow more efficient access to network while we have to work in multiple environments. working through the web is inefficient and increasing overhead costs |  | 2026-04-06 09:30 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-09 09:30 |  | GCC High Migration Support |  | INC0624420
INC0624415 | In Progress | Christine.Diehl@serco-na.com | How to forward email from commercial to GCCHi | Serco Business Good morning! Could someone please advise how you automatically forward email from our commercial email address to our GCCHi? Thank you. Christine Christine G. Diehl ¦ Serco ¦ Agile Impact Business Advisor 2661 Commons Blvd, Suite 100, Beavercreek, OH 45431 Mobile: 937-524-6455 E-mail: christine.diehl@serco-na.com<mailto:christine.diehl@serco-na.com> E-mail for CUI: christine.diehl@serco-na.us<mailto:christine.diehl@serco-na.us> Please note: as of 30 Mar all emails to me should use the CUI address: Christine.diehl@serco-na.us<mailto:Christine.diehl@serco-na.us>. Serco is migrating to all CUI emails, and will be shutting down my ability to receive emails at the .com address. This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | Jade Scherer | 2026-04-06 09:23 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-09 09:23 |  | GCC High Migration Support |  | INC0624415
INC0624413 | New | Scott.Adams@serco-na.com | There is no Sensitivity Ribbon when replying to (accepting, rejecting) meeting requests sent from non GCCH email sources. We cannot, therefore, select a label | There is no Sensitivity Ribbon when replying to (accepting, rejecting) meeting requests sent from non GCCH email sources. We cannot, therefore, select a label (such as "SB-unmarked" that will allow the response to cross from GCCH to non GCCH accounts. Accordingly, accepting or rejecting a meeting invite never gets to the person requesting the meeting, and there's no way to do so. |  | 2026-04-06 09:18 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-09 09:18 |  | GCC High Migration Support |  | INC0624413
INC0624410 | New | Christopher.Pritchet@serco-na.com | "Schedule a Teams Meeting" does not show on my Outlook ribbon bar and I do not know how to add it. Although I can schedule meetings on my GCCH account, I canno | "Schedule a Teams Meeting" does not show on my Outlook ribbon bar and I do not know how to add it. Although I can schedule meetings on my GCCH account, I cannot schedule virtual Teams meetings (w/ link, dial in #, etc.) as I have always been able to do in commercial Outlook. |  | 2026-04-06 09:07 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-09 09:07 |  | GCC High Migration Support |  | INC0624410
INC0624259 | In Progress | guest | GCCH Software Installation RITM0107017 | Serco Business - Non CUI I have a time sensitive software request. This is contractually required and funded by a customer and the customer requires the task to be completed in a very short time frame. Please help: [cid:image001.png@01DCC360.1214C4E0] | Jade Scherer | 2026-04-03 12:52 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-08 12:52 |  | GCC High Migration Support |  | INC0624259
INC0624255 | New | Christopher.Pritchet@serco-na.com | From my new GCCH laptop and using the AirForce EITaaS AVD (which connects fine), all NIPRNet emails I send to my serco-na.us (GCCH) account are rejected. Is not | From my new GCCH laptop and using the AirForce EITaaS AVD (which connects fine), all NIPRNet emails I send to my serco-na.us (GCCH) account are rejected. Is not part of the migration to a CUI environment back-and-forth communication between NIPRNet and GCC-H? |  | 2026-04-03 12:37 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-08 12:37 |  | GCC High Migration Support |  | INC0624255
INC0624249 | In Progress | James.Mathis@serco-na.com | Survey form for Migration is not working. | Serco Business I fill out number 1. And 2. Where do I go from there? This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | Jade Scherer | 2026-04-03 12:20 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-08 12:20 |  | GCC High Migration Support |  | INC0624249
INC0624198 | In Progress | Michael.Mcneill@serco-na.com | There is a proposal document in Teams on Serco.com and when I try to open it to edit, it ask for serco.com email, password and then it tells me "You cannot acce | There is a proposal document in Teams on Serco.com and when I try to open it to edit, it ask for serco.com email, password and then it tells me "You cannot access this right now". I can edit it in Teams, but after email a version to GCCH, the layout is off and I'm not able to edit it correctly and see accurate updates. This proposal has to be ready for review next week. Please let me know if this is something that can be fixed or if me and other proposal writers need to email it to GCCH and then back to Serco.com. Most folks on the team don't have GCCH laptops. Believe me and one other guy. Thanks for your help. | Jade Scherer | 2026-04-03 08:32 | TRUE | 2026-04-03 11:25:21 - Jade Scherer (Work notes) [code]Issue:<br>A user is experiencing issues accessing and editing a proposal document in Teams on Serco.com, receiving an access error after attempting to log in with Serco.com credentials. After emailing a version to GCCH, the layout becomes distorted, preventing accurate editing and updates. The proposal requires completion for review next week, and the user seeks resolution or guidance on workflow adjustments, noting that most team members lack GCCH laptops.​⁠⁠⁠​[/code] | 2026-04-03 11:25:21 - Jade Scherer (Work notes) [code]Issue:<br>A user is experiencing issues accessing and editing a proposal document in Teams on Serco.com, receiving an access error after attempting to log in with Serco.com credentials. After emailing a version to GCCH, the layout becomes distorted, preventing accurate editing and updates. The proposal requires completion for review next week, and the user seeks resolution or guidance on workflow adjustments, noting that most team members lack GCCH laptops.​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-08 08:32 |  | GCC High Migration Support |  | INC0624198
INC0624125 | In Progress | Kyle.Hagen@serco-na.com | Please see attached for multiple issues I'm experiencing. I also sent this to the GCCH Migration support email a few days ago. | Please see attached for multiple issues I'm experiencing. I also sent this to the GCCH Migration support email a few days ago. | Jade Scherer | 2026-04-02 14:23 | TRUE | 2026-04-03 11:13:35 - Jade Scherer (Work notes) [code]Issue:<br>A user is experiencing multiple issues, including being unable to send invites from their .US Outlook account that include a Teams meeting, and previously encountered a similar issue on the .COM side without the add-in available. The user also mentioned sending the same request to GCCH Migration support a few days ago.​⁠⁠⁠​[/code] | 2026-04-03 11:13:35 - Jade Scherer (Work notes) [code]Issue:<br>A user is experiencing multiple issues, including being unable to send invites from their .US Outlook account that include a Teams meeting, and previously encountered a similar issue on the .COM side without the add-in available. The user also mentioned sending the same request to GCCH Migration support a few days ago.​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-07 14:23 |  | GCC High Migration Support |  | INC0624125
INC0624102 | In Progress | Albert.Moseley@serco-na.com | INC0624101 | Serco Business I submitted a ticket for my inability to use any browser on my GCCH laptop. Can't get past the acknowledgement page in Edge and can't log in via Chrome. [A black background with grey letters and a red circle Description automatically generated] Albert G. Moseley IV, SHRM-SCP Principal, Agile Impact Serco North America, Advanced Solutions Group (ASG) T: 1-703-213-5893, M: 1-703-953-6123 Commercial/UNCLASS: albert.moseley@serco-na.com<mailto:albert.moseley@serco-na.com> CUI: albert.moseley@serco-na.us<mailto:albert.moseley@serco-na.us> ¦ www.serco.com/na<http://www.serco.com/na> LI: linkedin.com/in/allbert-moseley6845a313<https://www.linkedin.com/in/corina-mccormack-52001431/> This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | Jade Scherer | 2026-04-02 12:57 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-07 12:57 |  | GCC High Migration Support |  | INC0624102
INC0624095 | On Hold | Daniel.Mattioda@serco-na.com | Unable to Open and Download documents from Serco WINS site (example: https://serco.sharepoint.com/sites/SA-GE-WINS-US-32877-MG) | Unable to Open and Download documents from Serco WINS site (example: https://serco.sharepoint.com/sites/SA-GE-WINS-US-32877-MG) | Jade Scherer | 2026-04-02 12:24 | TRUE | 2026-04-02 14:49:29 - Jade Scherer (Work notes) Called user Shared screen User can access web apps but not desktop apps for Commercial SharePoint docs Reaching out to Sasha and Anthony for direction | 2026-04-02 14:49:29 - Jade Scherer (Work notes) Called user Shared screen User can access web apps but not desktop apps for Commercial SharePoint docs Reaching out to Sasha and Anthony for direction | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-07 12:24 |  | GCC High Migration Support |  | INC0624095
INC0624090 | On Hold | Christine.Diehl@serco-na.com | GCCHi password | Serco Business Good morning, Is my password for GCCHi account (.us) linked to/the same as my commercial account (.com)? I am trying to access a Sharepoint site on my GCCHi computer. It asks me to input my email and password, and then a Serco box comes back and says 'Your account or password is incorrect. If you don't remember your password, reset it now." I don't want to reset my GCCHi password if it is the same /linked to my commercial password and this will then screw up other accounts (like my timecard). Or is it that we cannot access any Serco websites on our GCCHi account using our .us email? Please advise. Thanks. Christine Christine G. Diehl ¦ Serco ¦ Agile Impact Business Advisor 2661 Commons Blvd, Suite 100, Beavercreek, OH 45431 Mobile: 937-524-6455 E-mail: christine.diehl@serco-na.com<mailto:christine.diehl@serco-na.com> E-mail for CUI: christine.diehl@serco-na.us<mailto:christine.diehl@serco-na.us> Please note: as of 30 Mar all emails to me should use the CUI address: Christine.diehl@serco-na.us<mailto:Christine.diehl@serco-na.us>. Serco is migrating to all CUI emails, and will be shutting down my ability to receive emails at the .com address. This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | Jade Scherer | 2026-04-02 12:12 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-07 12:12 |  | GCC High Migration Support |  | INC0624090
INC0624016 | In Progress | Ric.Simonis@serco-na.com | Upcoming GCCH Migration - Simonis | GCCH Migration Team, I have received and completed the survey for my migration to GCCH. However, I already physically have a GCCH laptop (Tag# T048902) that was issued to me for my role an alternate COMSEC manager. I still use my commercial laptop (Tag# 034096) day-to-day. How will this impact my migration? Please be advised that I'm on business travel next week. Emp# 80014318 Richard 'Ric' Simonis DRSN Installation Engineer III, SI2 Serco North America T: (719) 235-4265 M: (719) 649-6609 <mailto:ric.simonis@serco-na.com> ric.simonis@serco-na.com ¦ <http://www.serco-na.com/> www.serco.com/na | Jade Scherer | 2026-04-02 09:11 | TRUE | 2026-04-02 12:09:32 - Jade Scherer (Work notes) [code]Issue:<br>Richard 'Ric' Simonis, a DRSN Installation Engineer III, has inquired about the impact of using both a GCCH laptop (Tag# T048902) and a commercial laptop (Tag# 034096) day-to-day during his migration to GCCH, noting he will be on business travel the following week.<br><br>Key Actions Taken:<br>&emsp;- Received and acknowledged the incident report from Ric Simonis regarding GCCH migration concerns.<br>&emsp;- Forwarded the ticket to the Field Service Team for further support.<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 1<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: N/A<br>&emsp;&emsp;- Breach time: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Affected CIs: N/A<br>&emsp;- Impacted Services: N/A<br>&emsp;- Impacted Services/CIs: N/A​⁠⁠⁠​[/code] 2026-04-02 12:03:57 - Jade Scherer (Work notes) [code]Issue:<br>Richard 'Ric' Simonis, a DRSN Installation Engineer III, has inquired about the impact of using both a GCCH laptop (Tag# T048902) and a commercial laptop (Tag# 034096) day-to-day during his migration to GCCH, noting he will be on business travel the following week.<br><br>Key Actions Taken:<br>&emsp;- Received and acknowledged the user's query regarding GCCH migration and dual laptop usage.<br>&emsp;- Noted the user's business travel schedule for the upcoming week.<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 1<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: N/A<br>&emsp;&emsp;- Breach time: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Affected CIs: N/A<br>&emsp;- Impacted Services: N/A<br>&emsp;- Impacted Services/CIs: N/A​⁠⁠⁠​[/code] | 2026-04-02 12:09:32 - Jade Scherer (Work notes) [code]Issue:<br>Richard 'Ric' Simonis, a DRSN Installation Engineer III, has inquired about the impact of using both a GCCH laptop (Tag# T048902) and a commercial laptop (Tag# 034096) day-to-day during his migration to GCCH, noting he will be on business travel the following week.<br><br>Key Actions Taken:<br>&emsp;- Received and acknowledged the incident report from Ric Simonis regarding GCCH migration concerns.<br>&emsp;- Forwarded the ticket to the Field Service Team for further support.<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 1<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: N/A<br>&emsp;&emsp;- Breach time: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Affected CIs: N/A<br>&emsp;- Impacted Services: N/A<br>&emsp;- Impacted Services/CIs: N/A​⁠⁠⁠​[/code] 2026-04-02 12:03:57 - Jade Scherer (Work notes) [code]Issue:<br>Richard 'Ric' Simonis, a DRSN Installation Engineer III, has inquired about the impact of using both a GCCH laptop (Tag# T048902) and a commercial laptop (Tag# 034096) day-to-day during his migration to GCCH, noting he will be on business travel the following week.<br><br>Key Actions Taken:<br>&emsp;- Received and acknowledged the user's query regarding GCCH migration and dual laptop usage.<br>&emsp;- Noted the user's business travel schedule for the upcoming week.<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 1<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: N/A<br>&emsp;&emsp;- Breach time: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Affected CIs: N/A<br>&emsp;- Impacted Services: N/A<br>&emsp;- Impacted Services/CIs: N/A​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-07 09:11 |  | GCC High Migration Support |  | INC0624016
INC0623845 | On Hold | Wayne.Borchers@serco-na.com | GCC-H OneNote | Serco Business Migration Team, I need some assistance with my OneNote. I have found the .com notebook file in the .us OneDrive, but I am unable to use it within the .us environment since it says it's read-only. Any suggestions? [A black background with grey letters and a red circle Description automatically generated] Wayne P. Borchers, PMP Director, Acquisition Program Management Agile Impact T: (757) 350-6821 ¦ M: (757) 544-5618 wayne.borchers@serco-na.us<mailto:wayne.borchers@serco-na.us> ¦ www.serco.com<http://www.serco.com/> This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | Jade Scherer | 2026-04-01 11:53 | TRUE | 2026-04-02 14:29:49 - Benjamin Gould (Work notes) Hi Jade. Doesn't look like a migration issue since the data came over. If the notebook is in read-only, have the user check the OneNote properties on the location of the OneNote Could also try to open OneNote> File > Info> View Sync Status, then Sync All, then close re-open OneNote. If neither are working the user could open the Read-Only notebook in OneNote > File > New Then right click each section in the old notebook, select Move/Copy and move them to the new notebook and allow time for sync 2026-04-02 12:16:39 - Jade Scherer (Work notes) @Christopher Burns If this is not a migration issue, please reassign to me. | 2026-04-02 14:29:49 - Benjamin Gould (Work notes) Hi Jade. Doesn't look like a migration issue since the data came over. If the notebook is in read-only, have the user check the OneNote properties on the location of the OneNote Could also try to open OneNote> File > Info> View Sync Status, then Sync All, then close re-open OneNote. If neither are working the user could open the Read-Only notebook in OneNote > File > New Then right click each section in the old notebook, select Move/Copy and move them to the new notebook and allow time for sync 2026-04-02 12:16:39 - Jade Scherer (Work notes) @Christopher Burns If this is not a migration issue, please reassign to me. | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-06 11:53 |  | GCC High Migration Support |  | INC0623845
INC0623814 | New | David.Pine@serco-na.com | Need help running a SW update on GCC-H for APPGate | My GCC-H AppGate application has a SW update available. I have attempted to update several times, but get an failure error message. The existing SW is working so I am not impacted as yet. (just a few weeks ago they published a notice that if you weren't running version 6.4.1 or higher you would lose connectivity. I current have Version 6.4.1-39256-release Type: Full With a pending switch to a GCC-H laptop in the next few days, I was hoping to get this taken care of before the switch to prevent issues once I do shift to the new HW. David Pine T&E, Engineering SME, Serco - Agile Impact (A+) Serco - North America T: 757.350.4286 I M: 757.777.4738 David.pine@serco-na.com <mailto:David.pine@serco-na.com> I www.serco.com <http://www.serco.com> CUI: David.pine@sero-na.us <mailto:David.pine@sero-na.us> |  | 2026-04-01 10:45 | TRUE |  |  | 4656 |  | 3.08 | 146544 | 4656 |  | FALSE | 2026-04-06 10:45 |  | GCC High Migration Support |  | INC0623814
INC0623802 | In Progress | Christina.Hall@serco-na.com | "snipping tool" not working on GCCH....software is on computer. | "snipping tool" not working on GCCH....software is on computer. | Aaron Tang | 2026-04-01 10:20 | TRUE | 2026-04-03 11:14:03 - Jade Scherer (Work notes) [code]Issue:<br>The snipping tool is not functioning on a computer running GCCH, as reported by the user.​⁠⁠⁠​[/code] | 2026-04-03 11:14:03 - Jade Scherer (Work notes) [code]Issue:<br>The snipping tool is not functioning on a computer running GCCH, as reported by the user.​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-06 10:20 |  | GCC High Migration Support |  | INC0623802
INC0623801 | In Progress | Christina.Hall@serco-na.com | Internal Serco emails are being quarantined as SPAM. i.e. sercoglobal.com; serco engage | Internal Serco emails are being quarantined as SPAM. i.e. sercoglobal.com; serco engage | Aaron Tang | 2026-04-01 10:18 | TRUE | 2026-04-03 11:14:50 - Jade Scherer (Work notes) [code]Issue:<br>Internal Serco emails from domains such as sercoglobal.com and serco engage are being quarantined as SPAM.​⁠⁠⁠​[/code] | 2026-04-03 11:14:50 - Jade Scherer (Work notes) [code]Issue:<br>Internal Serco emails from domains such as sercoglobal.com and serco engage are being quarantined as SPAM.​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-06 10:18 |  | GCC High Migration Support |  | INC0623801
INC0623782 | On Hold | Christina.Hall@serco-na.com | my one note did not migrate from my .com, including my sticky notes. My understanding is you can change the ownership in one note, but that option is not availa | my one note did not migrate from my .com, including my sticky notes. My understanding is you can change the ownership in one note, but that option is not available to me, as it is a setting... | Robert Bartholomew | 2026-04-01 09:37 | TRUE | 2026-04-02 16:18:35 - John Hudson (Work notes) [code]Issue:<br>A user reported that their OneNote content, including sticky notes, did not migrate from their commercial (.com) account to the GCCH (.us) environment. The user was unable to change ownership in OneNote as the option was not available, and the GCCH OneNote environment appeared empty.<br><br>Key Actions Taken:<br>&emsp;- Verified the user is on a GCCH laptop<br>&emsp;- Confirmed OneNote data exists in the commercial (.com) account<br>&emsp;- Checked that the GCCH (.us) OneNote environment is empty<br>&emsp;- Reviewed Sticky Notes settings to confirm association with the .com account<br>&emsp;- Attempted to change ownership in OneNote (unsuccessful)<br>&emsp;- Attempted to contact the user via Microsoft Teams for further troubleshooting<br>&emsp;- Noted the user was out of office with no return date provided<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 3<br>&emsp;- Total number of breached SLAs: 1<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Completed: 1<br>&emsp;&emsp;- In progress: 1<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: Priority 3 response (4 hours)<br>&emsp;&emsp;- Breach time: 2026-04-01 13:37:08<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 22 Hours 19 Minutes<br><br>Affected CIs and Impacted Services:<br>&emsp;- Affected CIs: N/A<br>&emsp;- Impacted Services: N/A<br>&emsp;- Impacted Services/CIs: N/A​⁠⁠⁠​[/code] 2026-04-02 15:57:36 - Cedric Mearite (Work notes) [code]Issue:<br>A user reported that their OneNote content, including sticky notes, did not migrate from their commercial (.com) account to the GCCH (.us) environment. The user was unable to change ownership in OneNote as the option was not available, and the GCCH OneNote environment appeared empty.<br><br>Key Actions Taken:<br>&emsp;- Verified the user is on a GCCH laptop<br>&emsp;- Confirmed OneNote data exists in the commercial (.com) account<br>&emsp;- Checked that the GCCH (.us) OneNote environment is empty<br>&emsp;- Reviewed Sticky Notes settings to confirm association with the .com account<br>&emsp;- Attempted to change ownership in OneNote (unsuccessful)<br>&emsp;- Attempted to contact the user via Microsoft Teams for further troubleshooting<br>&emsp;- Noted the user was out of office with no return date provided<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 2<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Completed: 1<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: N/A<br>&emsp;&emsp;- Breach time: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 22 Hours 19 Minutes<br><br>Affected CIs and Impacted Services:<br>&emsp;- Impacted Services/CIs: N/A<br>&emsp;- Affected CIs: N/A​⁠⁠⁠​[/code] 2026-04-02 15:57:14 - Cedric Mearite (Work notes) Best Call Back Number(s): Best contact via Microsoft Teams (user appears offline but is responding to Teams messages) Best Call Time: ASAP Time Zone: EST Device Name: LAP5CG1382B3F LPG2MQ552071Q Error Message: User unable to access OneNote content in GCCH (.us). OneNote environment appears empty. Sticky Notes still tied to commercial (.com) account and user unable to change ownership. Prompt advises to contact IT/admin. Troubleshooting Steps: Verified user is on GCCH laptop Confirmed OneNote data exists in commercial (.com) account Confirmed GCCH (.us) OneNote is empty Reviewed Sticky Notes settings showing association with .com account Attempted ownership change (not available to user) Summary: OneNote and Sticky Notes did not migrate from .com to GCCH (.us). Data exists in commercial account but ownership did not transfer. Requires backend migration support. 2026-04-02 15:17:28 - Cedric Mearite (Work notes) User is currently out of office and has been OOO since 03/31. No return date has been provided at this time. Attempted to contact user via Microsoft Teams to begin troubleshooting and gather additional information regarding OneNote and Sticky Notes not migrating from .com to GCCH (.us). Requested user to verify data in commercial account and check availability in GCCH environment. Unable to proceed further with troubleshooting until user is available. Will follow up once user returns or if additional information is received. | 2026-04-02 16:18:35 - John Hudson (Work notes) [code]Issue:<br>A user reported that their OneNote content, including sticky notes, did not migrate from their commercial (.com) account to the GCCH (.us) environment. The user was unable to change ownership in OneNote as the option was not available, and the GCCH OneNote environment appeared empty.<br><br>Key Actions Taken:<br>&emsp;- Verified the user is on a GCCH laptop<br>&emsp;- Confirmed OneNote data exists in the commercial (.com) account<br>&emsp;- Checked that the GCCH (.us) OneNote environment is empty<br>&emsp;- Reviewed Sticky Notes settings to confirm association with the .com account<br>&emsp;- Attempted to change ownership in OneNote (unsuccessful)<br>&emsp;- Attempted to contact the user via Microsoft Teams for further troubleshooting<br>&emsp;- Noted the user was out of office with no return date provided<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 3<br>&emsp;- Total number of breached SLAs: 1<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Completed: 1<br>&emsp;&emsp;- In progress: 1<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: Priority 3 response (4 hours)<br>&emsp;&emsp;- Breach time: 2026-04-01 13:37:08<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 22 Hours 19 Minutes<br><br>Affected CIs and Impacted Services:<br>&emsp;- Affected CIs: N/A<br>&emsp;- Impacted Services: N/A<br>&emsp;- Impacted Services/CIs: N/A​⁠⁠⁠​[/code] 2026-04-02 15:57:36 - Cedric Mearite (Work notes) [code]Issue:<br>A user reported that their OneNote content, including sticky notes, did not migrate from their commercial (.com) account to the GCCH (.us) environment. The user was unable to change ownership in OneNote as the option was not available, and the GCCH OneNote environment appeared empty.<br><br>Key Actions Taken:<br>&emsp;- Verified the user is on a GCCH laptop<br>&emsp;- Confirmed OneNote data exists in the commercial (.com) account<br>&emsp;- Checked that the GCCH (.us) OneNote environment is empty<br>&emsp;- Reviewed Sticky Notes settings to confirm association with the .com account<br>&emsp;- Attempted to change ownership in OneNote (unsuccessful)<br>&emsp;- Attempted to contact the user via Microsoft Teams for further troubleshooting<br>&emsp;- Noted the user was out of office with no return date provided<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 2<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Completed: 1<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: N/A<br>&emsp;&emsp;- Breach time: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 22 Hours 19 Minutes<br><br>Affected CIs and Impacted Services:<br>&emsp;- Impacted Services/CIs: N/A<br>&emsp;- Affected CIs: N/A​⁠⁠⁠​[/code] 2026-04-02 15:57:14 - Cedric Mearite (Work notes) Best Call Back Number(s): Best contact via Microsoft Teams (user appears offline but is responding to Teams messages) Best Call Time: ASAP Time Zone: EST Device Name: LAP5CG1382B3F LPG2MQ552071Q Error Message: User unable to access OneNote content in GCCH (.us). OneNote environment appears empty. Sticky Notes still tied to commercial (.com) account and user unable to change ownership. Prompt advises to contact IT/admin. Troubleshooting Steps: Verified user is on GCCH laptop Confirmed OneNote data exists in commercial (.com) account Confirmed GCCH (.us) OneNote is empty Reviewed Sticky Notes settings showing association with .com account Attempted ownership change (not available to user) Summary: OneNote and Sticky Notes did not migrate from .com to GCCH (.us). Data exists in commercial account but ownership did not transfer. Requires backend migration support. 2026-04-02 15:17:28 - Cedric Mearite (Work notes) User is currently out of office and has been OOO since 03/31. No return date has been provided at this time. Attempted to contact user via Microsoft Teams to begin troubleshooting and gather additional information regarding OneNote and Sticky Notes not migrating from .com to GCCH (.us). Requested user to verify data in commercial account and check availability in GCCH environment. Unable to proceed further with troubleshooting until user is available. Will follow up once user returns or if additional information is received. | 70832 |  | 46.85 | 80368 | 106832 |  | FALSE | 2026-04-06 09:37 |  | GCC High Migration Support |  | INC0623782
INC0623689 | On Hold | Deborah.Linton@serco-na.com | AutoDesk Navisworks | Serco Business Subject s/w is installed on my GCCH laptop but does not function. Returns a continuous screen of "Searching for the latest updates and features..." for hours on end. Debbie Linton Aero Engineer - System Architect, Serco-North America Office: 850.739.4873 ¦ Mobile: 301.247.0870 E-mail: deborah.linton@serco-na.com<mailto:deborah.linton@serco-na.com> NIPR: deborah.linton.ctr@us.af.mil<mailto:deborah.linton.ctr@us.af.mil> This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | Ismar Yepez | 2026-03-31 16:21 | TRUE | 2026-04-02 12:34:19 - Jade Scherer (Work notes) [code]Issue:<br>Debbie Linton reported that AutoDesk Navisworks software installed on her GCCH laptop is malfunctioning, displaying a continuous screen stating 'Searching for the latest updates and features...' for extended periods.<br><br>Key Actions Taken:<br>&emsp;- Received the incident report from Deborah Linton via email, including details about the software issue and contact information<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 1<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Affected CIs: N/A<br>&emsp;- Impacted Services: N/A<br>&emsp;- Impacted Services/CIs: N/A​⁠⁠⁠​[/code] | 2026-04-02 12:34:19 - Jade Scherer (Work notes) [code]Issue:<br>Debbie Linton reported that AutoDesk Navisworks software installed on her GCCH laptop is malfunctioning, displaying a continuous screen stating 'Searching for the latest updates and features...' for extended periods.<br><br>Key Actions Taken:<br>&emsp;- Received the incident report from Deborah Linton via email, including details about the software issue and contact information<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 1<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Affected CIs: N/A<br>&emsp;- Impacted Services: N/A<br>&emsp;- Impacted Services/CIs: N/A​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-03 16:21 |  | GCC High Migration Support |  | INC0623689
INC0623639 | In Progress | guest | Calling From GCCH Teams | Serco Business - Non CUI Good afternoon, My GCCH "Calls" tab shows my correct work number. However, when I try to call a fellow Serco-NA employee via desktop Teams app and they are on the .com side, it goes straight to Voicemail and does not ring through. I immediately tried the individual on my .com Teams and was able to connect fine. I can successfully make a Teams call to another .us account. Is there a reason why I cannot call from .us to a .com person on Teams? Thank you, Tim | Jade Scherer | 2026-03-31 14:01 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-03 14:01 |  | GCC High Migration Support |  | INC0623639
INC0623637 | In Progress | Deborah.Linton@serco-na.com | One Note notes needed | Serco Business My One Notes did not migrate over from my commercial side. Perhaps this will happen when Teams fully migrates? Thank you, Debbie Linton Aero Engineer - System Architect, Serco-North America Office: 850.739.4873 ¦ Mobile: 301.247.0870 E-mail: deborah.linton@serco-na.com<mailto:deborah.linton@serco-na.com> NIPR: deborah.linton.ctr@us.af.mil<mailto:deborah.linton.ctr@us.af.mil> This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | Christopher Burns | 2026-03-31 13:43 | TRUE | 2026-04-03 16:03:44 - Jade Scherer (Work notes) @Christopher Burns Please reassign this to me if this is not a migration issue you handle. | 2026-04-03 16:03:44 - Jade Scherer (Work notes) @Christopher Burns Please reassign this to me if this is not a migration issue you handle. | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-03 13:43 |  | GCC High Migration Support |  | INC0623637
INC0623634 | In Progress | guest | CUI printer mapping | Serco Business - Non CUI I was following the instructions to map printer PRN-HRN-7F-C8255 to my new GCCH laptop. Unfortunately, I entered a 4-digit code when it gave me that option, without reading done tat Serco had set 6 digits as a policy. The printer deleted the job as a result. However, I cannot find a way to go back and change the code to 6 digits for this or any other jobs. I have tried closing and opening apps and removing and reselecting the printer. Is there a way to reset this? Bill Montgomery Manager Serco Inc. T: 703.214.0803 M: 571.243.3113 william.montgomery@serco-na.us<mailto:john.smith@serco-na.com> www.serco-na.com<http://www.serco-na.com/> [cid:image001.png@01DCC112.47276B10] | Aaron Tang | 2026-03-31 13:34 | TRUE | 2026-04-03 16:02:32 - Jade Scherer (Work notes) @Aaron Tang Please assist user with resetting up their PIN | 2026-04-03 16:02:32 - Jade Scherer (Work notes) @Aaron Tang Please assist user with resetting up their PIN | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-03 13:34 |  | GCC High Migration Support |  | INC0623634
INC0623633 | In Progress | guest | IMMEDIATE ATTENTION NEEDED; Teams Add In Outlook GCC-H | Serco Business - Non CUI Hello - I believe the Microsoft Teams add on in Outlook does not work on GGG-H. Since the weekend migration activities, I can no longer put a Teams link in the body of a meeting invite I am trying to create. There is no button to press at the top when creating the Teams meeting to give invited individuals the ability to join a meeting. I was able to schedule a meeting normally (Teams link in the body of the email) last Friday on GCC-H but the migration activities over the weekend seem to have created an issue. If I am correct, this needs immediate attention and may be impacting many others. If I am wrong, please tell me how to put a Teams link in a meeting invite in Outlook on GCC-H. I have done it countless times on the commercial side with no issue. I submitted a ticket on this but appreciate someone's immediate attention to resolving this issue. I cannot move projects along with my team without being able to invite them to meetings where they can participate virtually. Thanks. [cid:image001.png@01DCC112.B3987F00] | Jade Scherer | 2026-03-31 13:34 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-03 13:34 |  | GCC High Migration Support |  | INC0623633
INC0623631 | Resolved | William.Burnette@serco-na.com | The Teams add-in to Outlook allowing us to schedule a teams meeting from within Outlook is missing. It was there Friday, but is now gone. I have been migrated t | The Teams add-in to Outlook allowing us to schedule a teams meeting from within Outlook is missing. It was there Friday, but is now gone. I have been migrated to from .com to .us. | William Alexander | 2026-03-31 13:33 | TRUE | 2026-04-02 16:31:28 - Jade Scherer (Work notes) @William Alexander Will please see Danielle's note on this yesterday | 2026-04-02 16:31:28 - Jade Scherer (Work notes) @William Alexander Will please see Danielle's note on this yesterday | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-03 13:33 |  | GCC High Migration Support |  | INC0623631
INC0623626 | On Hold | Rebecca.Dunlap@serco-na.com | One of the compressed/zipped folders transferred from Northrop Grumman cannot be opened - error message is attached | One of the compressed/zipped folders transferred from Northrop Grumman cannot be opened - error message is attached | William Alexander | 2026-03-31 13:25 | TRUE | 2026-04-02 16:28:20 - Jade Scherer (Work notes) @William Alexander Please get the error from user and troubleshoot. | 2026-04-02 16:28:20 - Jade Scherer (Work notes) @William Alexander Please get the error from user and troubleshoot. | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-03 13:25 |  | GCC High Migration Support |  | INC0623626
INC0623621 | In Progress | guest | Access to Citrix in the Company Portal | I know Tim Hope has been working on this effort and Brock Magnino has been communicating with Sasha and Cheryl but since this is still a known issue, I wanted to track it. I need Citrix to access the link below for DHS remote desktop. We were told this would originally be pushed on 3/23 to our company portal and we have not yet received it. Please advise so that we are able to login to DHS remote desktop. Thank you, ~Courtney quickconnect.dhs.gov/Citrix/DC-1-WANWeb/ [cid:image001.png@01DCC10F.FD35BD60] | Ismar Yepez | 2026-03-31 13:17 | TRUE | 2026-04-03 11:53:31 - Jade Scherer (Work notes) @Ismar Yepez This issue for Courtney Kelly 2026-04-03 11:44:36 - Jade Scherer (Work notes) @Ismar Yepez Are you able to assist with Citrix issue | 2026-04-03 11:53:31 - Jade Scherer (Work notes) @Ismar Yepez This issue for Courtney Kelly 2026-04-03 11:44:36 - Jade Scherer (Work notes) @Ismar Yepez Are you able to assist with Citrix issue | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-03 13:17 |  | GCC High Migration Support |  | INC0623621
INC0623605 | In Progress | Timothy.Winand@serco-na.com | I do not see any ability to schedule a Teams meeting in Outlook. When I open up a new meeting, I do not see a "Teams Meeting" button to click to add the Teams l | I do not see any ability to schedule a Teams meeting in Outlook. When I open up a new meeting, I do not see a "Teams Meeting" button to click to add the Teams link to the body of the meeting invite. I need some help on this ASAP as I can't move any projects along if I can't have virtual meetings. | Jade Scherer | 2026-03-31 12:38 | TRUE | 2026-04-03 11:32:32 - Jade Scherer (Work notes) [code]Issue:<br>A user is unable to schedule a Teams meeting in Outlook due to the absence of a 'Teams Meeting' button when creating a new meeting, which prevents adding a Teams link to the meeting invite. The user emphasizes the impact on project momentum and requests immediate attention.​⁠⁠⁠​[/code] | 2026-04-03 11:32:32 - Jade Scherer (Work notes) [code]Issue:<br>A user is unable to schedule a Teams meeting in Outlook due to the absence of a 'Teams Meeting' button when creating a new meeting, which prevents adding a Teams link to the meeting invite. The user emphasizes the impact on project momentum and requests immediate attention.​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-03 12:38 |  | GCC High Migration Support |  | INC0623605
INC0623534 | In Progress | Daniel.Mattioda@serco-na.com | Request Adobe Reader added to Company Portal so I can download to my GCCH computer. | Request Adobe Reader added to Company Portal so I can download to my GCCH computer. | Ismar Yepez | 2026-03-31 09:22 | TRUE | 2026-04-03 11:16:06 - Jade Scherer (Work notes) @Ismar Yepez Software request. | 2026-04-03 11:16:06 - Jade Scherer (Work notes) @Ismar Yepez Software request. | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-03 09:22 |  | GCC High Migration Support |  | INC0623534
INC0623512 | Resolved | guest | quicksearch.dla.mil | This site is blocked from GCCH and I need it for my work with NAVSEA 05S. Greg Owens Cybersecurity SME (719) 359-7189 greg.owens@serco-na.us<mailto:greg.owens@serco-na.us> (GCC High) gregory.g.owens.ctr@us.navy.mil<mailto:gregory.g.owens.ctr@us.navy.mil> [cid:image001.png@01DCC0E7.4B66A9F0] | William Alexander | 2026-03-31 08:22 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-03 08:22 |  | GCC High Migration Support |  | INC0623512
INC0623511 | Resolved | Christopher.Pritchet@serco-na.com | I am not receiving emails sent using my serco-na.com address to my new GCCH laptop. Shouldn't these be forwarding? | I am not receiving emails sent using my serco-na.com address to my new GCCH laptop. Shouldn't these be forwarding? | William Alexander | 2026-03-31 08:20 | TRUE | 2026-04-03 11:17:24 - Jade Scherer (Work notes) @William Alexander Please confirm that they've setup their forwarding rule. | 2026-04-03 11:17:24 - Jade Scherer (Work notes) @William Alexander Please confirm that they've setup their forwarding rule. | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-03 08:20 |  | GCC High Migration Support |  | INC0623511
INC0623474 | In Progress | Charles.Dewar@serco-na.com | Since the migration of Outlook and OneDrive over this past weekend I can no longer send e-mails on High. Attached responses received from the AI shop. Additio | Since the migration of Outlook and OneDrive over this past weekend I can no longer send e-mails on High. Attached responses received from the AI shop. Additionally, I could not complete any actions on the migration site on Friday. | Jade Scherer | 2026-03-30 20:47 | TRUE | 2026-04-03 11:22:55 - Jade Scherer (Work notes) [code]Issue:<br>A user is experiencing issues with sending emails and accessing the migration site after the migration of Outlook and OneDrive over the past weekend, with confirmation that their .com and .us Outlook accounts are not linked.​⁠⁠⁠​[/code] | 2026-04-03 11:22:55 - Jade Scherer (Work notes) [code]Issue:<br>A user is experiencing issues with sending emails and accessing the migration site after the migration of Outlook and OneDrive over the past weekend, with confirmation that their .com and .us Outlook accounts are not linked.​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-02 20:47 |  | GCC High Migration Support |  | INC0623474
INC0623426 | Resolved | Michael.Mcneill@serco-na.com | Windows Activation Error | Serco Business Hello, I can’t setup my headphones to talk and at the top it tells me to Activate Windows. When I click on “install” it gives me the below message. I can hear in teams meetings but can’t talk and the System>Sound under “Settings” will is blacked out, can’t click on anything. Below is the message I get. Thanks for your support. We can’t activate Windows on this device as we can’t connect to your organization’s activation server. Make sure you’re connected to your organization’s network and try again. If you continue having problems with activation, contact your organization’s support person. Error code: 0x8007232B This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | John Hudson | 2026-03-30 15:47 | TRUE | 2026-03-31 15:26:00 - John Hudson (Work notes) Called end-user and left a voicemail message and informed him to do a Windows Update. Awaiting end-user to call back. | 2026-03-31 15:26:00 - John Hudson (Work notes) Called end-user and left a voicemail message and informed him to do a Windows Update. Awaiting end-user to call back. | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-02 15:47 |  | GCC High Migration Support |  | INC0623426
INC0623391 | Resolved | Deborah.Linton@serco-na.com | Cameo 2022x missing | Serco Business Please install Cameo Enterprise Architecture 2022x Refresh 2 Hotfix 3 into the Company Portal for me. It was on my GCCH previously and was listed on my original request form. Thank you. Debbie Linton Aero Engineer - System Architect, Serco-North America 962 West John Sims Parkway, Suite 100, Niceville FL 32578 Office: 850.739.4873 ¦ Mobile: 301.247.0870 E-mail: deborah.linton@serco-na.com<mailto:deborah.linton@serco-na.com> NIPR: deborah.linton.ctr@us.af.mil<mailto:deborah.linton.ctr@us.af.mil> This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | William Alexander | 2026-03-30 14:06 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-02 14:06 |  | GCC High Migration Support |  | INC0623391
INC0623390 | Resolved | Brian.Godfrey@serco-na.com | I included some of the software I needed to be loaded on my GCC-H in the survey, but there is one I forgot to include...FoxIt Editor. I did not see it in the Co | I included some of the software I needed to be loaded on my GCC-H in the survey, but there is one I forgot to include...FoxIt Editor. I did not see it in the Company Portal. Can I get that loaded? | Ismar Yepez | 2026-03-30 14:06 | TRUE | 2026-04-02 16:30:40 - Jade Scherer (Work notes) @Ismar Yepez Here's a software request. | 2026-04-02 16:30:40 - Jade Scherer (Work notes) @Ismar Yepez Here's a software request. | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-02 14:06 |  | GCC High Migration Support |  | INC0623390
INC0623337 | Resolved | Edward.Goehe@serco-na.com | MIGRATION ISSUE FOR ONEDRIVE. Many Onedrive Commercial Files did not transfer. Folders show but they are empty! Need fixing. I completed this in rgistry and se | MIGRATION ISSUE FOR ONEDRIVE. Many Onedrive Commercial Files did not transfer. Folders show but they are empty! Need fixing. I completed this in rgistry and selected No for not complete but Monday I still got emails saying migration was complete and Iam still haveing the Onedrive issue | Benjamin Gould | 2026-03-30 12:30 | TRUE |  |  | 7040 |  | 4.66 | 144160 | 7040 |  | FALSE | 2026-04-02 12:30 |  | GCC High Migration Support |  | INC0623337
INC0623322 | Resolved | Thomas.Glass@serco-na.com | FoxIt Editor is not installed, but was requested. Do I need to submit a SW request? | FoxIt Editor is not installed, but was requested. Do I need to submit a SW request? | Ismar Yepez | 2026-03-30 12:10 | TRUE | 2026-04-02 16:30:04 - Jade Scherer (Work notes) @Ismar Yepez Here's a software request. Please comment below. | 2026-04-02 16:30:04 - Jade Scherer (Work notes) @Ismar Yepez Here's a software request. Please comment below. | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-02 12:10 |  | GCC High Migration Support |  | INC0623322
INC0623301 | Resolved | Christine.Diehl@serco-na.com | GCCHi accound and NIPR Access | Serco Business Good morning - I am one of the employees in the pilot migration. We were asked if we needed NIPR connection, and I was too new to understand we could access NIPR through our SERCO laptops. I just received my CAC and was unaware of being able to access NIPR stuff through SERCO computers until I had a conversation last week with a co-worker. I believe I need EITASS. I have both the Windows App and Remote Desktop installed on my commercial account (so I could get to GCCHi. Only the Windows App allowed me access). Could you please help me so that I will be able to get to EITASS on my GCCHi laptop? Thank you. Christine Christine G. Diehl ¦ Serco ¦ Agile Impact Business Advisor 2661 Commons Blvd, Suite 100, Beavercreek, OH 45431 Mobile: 937-524-6455 E-mail: christine.diehl@serco-na.com<mailto:christine.diehl@serco-na.com> E-mail for CUI: christine.diehl@serco-na.us<mailto:christine.diehl@serco-na.us> Please note: as of 30 Mar all emails to me should use the CUI address: Christine.diehl@serco-na.us<mailto:Christine.diehl@serco-na.us>. Serco is migrating to all CUI emails, and will be shutting down my ability to receive emails at the .com address. This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | William Alexander | 2026-03-30 11:32 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-02 11:32 |  | GCC High Migration Support |  | INC0623301
INC0623248 | On Hold | guest | SercoNA.com Global Address Book Access | Serco Business - Non CUI Is there a way to get access to the Serco-NA.com global address book from my GCCH outlook account? | William Alexander | 2026-03-30 10:18 | TRUE | 2026-04-02 16:19:40 - Jade Scherer (Work notes) @William Alexander Can you please provide support. I believe these two environments are separate from each other. 2026-03-31 10:28:58 - Benjamin Gould (Work notes) Not a migration related issue | 2026-04-02 16:19:40 - Jade Scherer (Work notes) @William Alexander Can you please provide support. I believe these two environments are separate from each other. 2026-03-31 10:28:58 - Benjamin Gould (Work notes) Not a migration related issue | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-02 10:18 |  | GCC High Migration Support |  | INC0623248
INC0623205 | Resolved | Scott.Adams@serco-na.com | My MS Teams and channels need to be migrated to GCCH. Thank you. | My MS Teams and channels need to be migrated to GCCH. Thank you. | Christopher Burns | 2026-03-30 08:59 | TRUE | 2026-04-02 15:20:59 - Jade Scherer (Work notes) [code]Issue:<br>A case was opened regarding the need to migrate MS Teams and channels to GCCH, with a priority level of 3 - Medium.<br><br>Key Actions Taken:<br>&emsp;- The customer reported the requirement to migrate MS Teams and channels to GCCH via an activity comment on 30/03/2026 08:58:55.<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 2<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Completed: 1<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: N/A<br>&emsp;&emsp;- Breach time: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Impacted Services/CIs: N/A<br>&emsp;- Affected CIs: N/A​⁠⁠⁠​[/code] | 2026-04-02 15:20:59 - Jade Scherer (Work notes) [code]Issue:<br>A case was opened regarding the need to migrate MS Teams and channels to GCCH, with a priority level of 3 - Medium.<br><br>Key Actions Taken:<br>&emsp;- The customer reported the requirement to migrate MS Teams and channels to GCCH via an activity comment on 30/03/2026 08:58:55.<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 2<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Completed: 1<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: N/A<br>&emsp;&emsp;- Breach time: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Impacted Services/CIs: N/A<br>&emsp;- Affected CIs: N/A​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-02 08:59 |  | GCC High Migration Support |  | INC0623205
INC0623098 | On Hold | Daniel.Mattioda@serco-na.com | Unable to add GCC-H printers to GCC-H laptop. Type \\azgprdwprn02 in Windows Search bar of GCC-H laptop and nothing happens. | Unable to add GCC-H printers to GCC-H laptop. Type \\azgprdwprn02 in Windows Search bar of GCC-H laptop and nothing happens. | Aaron Tang | 2026-03-27 14:49 | TRUE | 2026-04-03 08:57:01 - Aaron Tang (Work notes) email sent. 2026-04-02 16:12:55 - Jade Scherer (Work notes) [code]Issue:<br>A user reported being unable to add GCC-H printers to their GCC-H laptop by typing \azgprdwprn02 in the Windows Search bar, with the issue initially reported on 27/03/2026. The user later confirmed resolution on 31/03/2026 after following steps in KB0010824.<br><br>Key Actions Taken:<br>&emsp;- User confirmed following steps in KB0010824 to add a printer but could not complete the process (30/03/2026).<br>&emsp;- User reported resolution on 31/03/2026 after successfully adding the printer and printing test pages.<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 3<br>&emsp;- Total number of breached SLAs: 1<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Completed: 1<br>&emsp;&emsp;- In progress: 1<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: Priority 3 response (4 hours)<br>&emsp;&emsp;- Breach time: 27/03/2026 18:48:53<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 7 Hours 7 Minutes<br><br>Affected CIs and Impacted Services:<br>&emsp;- Affected CIs: N/A<br>&emsp;- Impacted Services: N/A<br>&emsp;- Impacted Services/CIs: N/A​⁠⁠⁠​[/code] 2026-03-30 13:16:23 - Bradley Tucker (Work notes) User confirmed they are following the steps outlined in KB0010824 to add a printer but are unable to complete this process on their GCCH laptop. 2026-03-27 16:24:08 - Jade Scherer (Work notes) [code]Issue:<br>A user is unable to add GCC-H printers to a GCC-H laptop by typing \azgprdwprn02 in the Windows Search bar, resulting in no response.​⁠⁠⁠​[/code] | 2026-04-03 08:57:01 - Aaron Tang (Work notes) email sent. 2026-04-02 16:12:55 - Jade Scherer (Work notes) [code]Issue:<br>A user reported being unable to add GCC-H printers to their GCC-H laptop by typing \azgprdwprn02 in the Windows Search bar, with the issue initially reported on 27/03/2026. The user later confirmed resolution on 31/03/2026 after following steps in KB0010824.<br><br>Key Actions Taken:<br>&emsp;- User confirmed following steps in KB0010824 to add a printer but could not complete the process (30/03/2026).<br>&emsp;- User reported resolution on 31/03/2026 after successfully adding the printer and printing test pages.<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 3<br>&emsp;- Total number of breached SLAs: 1<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Completed: 1<br>&emsp;&emsp;- In progress: 1<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: Priority 3 response (4 hours)<br>&emsp;&emsp;- Breach time: 27/03/2026 18:48:53<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 7 Hours 7 Minutes<br><br>Affected CIs and Impacted Services:<br>&emsp;- Affected CIs: N/A<br>&emsp;- Impacted Services: N/A<br>&emsp;- Impacted Services/CIs: N/A​⁠⁠⁠​[/code] 2026-03-30 13:16:23 - Bradley Tucker (Work notes) User confirmed they are following the steps outlined in KB0010824 to add a printer but are unable to complete this process on their GCCH laptop. 2026-03-27 16:24:08 - Jade Scherer (Work notes) [code]Issue:<br>A user is unable to add GCC-H printers to a GCC-H laptop by typing \azgprdwprn02 in the Windows Search bar, resulting in no response.​⁠⁠⁠​[/code] | 39148 | 5715 | 25.89 | 112052 | 247948 |  | FALSE | 2026-04-01 14:49 | 5715 | GCC High Migration Support |  | INC0623098
INC0623095 | Resolved | Daniel.Mattioda@serco-na.com | Unable to access daniel.mattioda@serco-na.com Teams using the GCC-H Edge browser (https://www.office.com/) link. Outlook and OneDrive are accessible. | Unable to access daniel.mattioda@serco-na.com Teams using the GCC-H Edge browser (https://www.office.com/) link. Outlook and OneDrive are accessible. | Christopher Burns | 2026-03-27 14:41 | TRUE | 2026-03-27 16:22:23 - Jade Scherer (Work notes) [code]Issue:<br>Daniel Mattioda is unable to access their daniel.mattioda@serco-na.com Teams account using the GCC-H Edge browser via the https://www.office.com/ URL, while Outlook and OneDrive remain accessible.​⁠⁠⁠​[/code] | 2026-03-27 16:22:23 - Jade Scherer (Work notes) [code]Issue:<br>Daniel Mattioda is unable to access their daniel.mattioda@serco-na.com Teams account using the GCC-H Edge browser via the https://www.office.com/ URL, while Outlook and OneDrive remain accessible.​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-01 14:41 |  | GCC High Migration Support |  | INC0623095
INC0623094 | Resolved | Daniel.Mattioda@serco-na.com | daniel.mattioda@serco-na.com OneDrive files not migrated to daniel.mattioda@serco-na.us OneDrive account | daniel.mattioda@serco-na.com OneDrive files not migrated to daniel.mattioda@serco-na.us OneDrive account | Benjamin Gould | 2026-03-27 14:38 | TRUE | 2026-03-27 16:22:01 - Jade Scherer (Work notes) [code]Issue:<br>Daniel Mattioda reported that OneDrive files were not migrated to his daniel.mattioda@serco-na.us OneDrive account, as indicated in the case details and activity stream.​⁠⁠⁠​[/code] | 2026-03-27 16:22:01 - Jade Scherer (Work notes) [code]Issue:<br>Daniel Mattioda reported that OneDrive files were not migrated to his daniel.mattioda@serco-na.us OneDrive account, as indicated in the case details and activity stream.​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-01 14:38 |  | GCC High Migration Support |  | INC0623094
INC0623093 | Resolved | Daniel.Mattioda@serco-na.com | daniel.mattioda@serco-na.com Outlook Exchange files not migrated to daniel.mattioda@serco-na.us Outlook Exchange account | daniel.mattioda@serco-na.com Outlook Exchange files not migrated to daniel.mattioda@serco-na.us Outlook Exchange account | Benjamin Gould | 2026-03-27 14:37 | TRUE | 2026-03-27 16:21:35 - Jade Scherer (Work notes) [code]Issue:<br>Daniel Mattioda reported that Outlook Exchange files were not migrated to his new Outlook Exchange account at daniel.mattioda@serco-na.us.​⁠⁠⁠​[/code] | 2026-03-27 16:21:35 - Jade Scherer (Work notes) [code]Issue:<br>Daniel Mattioda reported that Outlook Exchange files were not migrated to his new Outlook Exchange account at daniel.mattioda@serco-na.us.​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-01 14:37 |  | GCC High Migration Support |  | INC0623093
INC0623074 | Resolved | Michael.Mcneill@serco-na.com | Need a wired hub for keyboard/mouse/CAC reader, most work is done on NIPR and current have to disconnect USB that controls keyboard and mouse to plug in CAC rea | Need a wired hub for keyboard/mouse/CAC reader, most work is done on NIPR and current have to disconnect USB that controls keyboard and mouse to plug in CAC reader. Thank you. | David Clinton | 2026-03-27 12:37 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-04-01 12:37 |  | GCC High Migration Support |  | INC0623074
INC0622813 | Resolved | Evan.Perreault@serco-na.com | I see that the Spotify URL (https://www.spotify.com) or the Spotify Web Player (https://open.spotify.com) is Blocked on GCCH web browser, where as it is current | I see that the Spotify URL (https://www.spotify.com) or the Spotify Web Player (https://open.spotify.com) is Blocked on GCCH web browser, where as it is currently accessible and not blocked on the .com side browser. I want to know why it is blocked, and how to get this unblocked or what the process is for requesting a URL to be unblocked is on GCCH. I listen to music all the time while I am working and would like to continue to do so when I eventually am made to transition to the GCCH laptop. | William Alexander | 2026-03-26 09:47 | TRUE | 2026-03-27 14:59:49 - Jade Scherer (Work notes) Assigned to myself | 2026-03-27 14:59:49 - Jade Scherer (Work notes) Assigned to myself | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-03-31 09:47 |  | GCC High Migration Support |  | INC0622813
INC0622695 | Resolved | Wayne.Borchers@serco-na.com | Need Co-Pilot | Serco Business I cannot find the .com licensed copy of Co-Pilot on my GCC-H laptop. I had requested that it be brought over. Can I get it installed since I use it daily? R, Wayne [A black background with grey letters and a red circle Description automatically generated] Wayne P. Borchers, PMP Director, Acquisition Program Management Agile Impact T: (757) 350-6821 ¦ M: (757) 544-5618 wayne.borchers@serco-na.com<mailto:wayne.borchers@serco-na.com> ¦ www.serco.com<http://www.serco.com/> This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | William Alexander | 2026-03-25 15:43 | TRUE |  |  | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-03-30 15:43 |  | GCC High Migration Support |  | INC0622695
INC0622635 | Resolved | Michael.Mcneill@serco-na.com | Monitor, mouse and keyboard | Serco Business I have a larger monitor on my current .com laptop, with a keyboard and mouse. The monitor is HDMI cable and the keyboard and mouse is a USB plug in. Do I need a ticket for you guys to turn on USB port and HDMI? Thank you. Mike This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | David Clinton | 2026-03-25 12:34 | TRUE | 2026-03-27 15:18:44 - David Clinton (Work notes) Contacted Michael to let him know there is no need for a USB waiver as his monitor, keyboard and mice should be a plug and play to his GCCH machine. He will let me know if it works. 2026-03-27 13:22:15 - Jade Scherer (Work notes) @David Clinton Does this require a USB waiver for GCCH laptops? | 2026-03-27 15:18:44 - David Clinton (Work notes) Contacted Michael to let him know there is no need for a USB waiver as his monitor, keyboard and mice should be a plug and play to his GCCH machine. He will let me know if it works. 2026-03-27 13:22:15 - Jade Scherer (Work notes) @David Clinton Does this require a USB waiver for GCCH laptops? | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-03-30 12:34 |  | GCC High Migration Support |  | INC0622635
INC0622634 | Resolved | guest | One Drive | Not all of my data on OneDrive was migrated over. Some of it was, but not all . Kind of hit and miss. Greg Owens Cybersecurity SME (719) 359-7189 greg.owens@serco-na.us<mailto:greg.owens@serco-na.us> (GCC High) gregory.g.owens.ctr@us.navy.mil<mailto:gregory.g.owens.ctr@us.navy.mil> [cid:image001.png@01DCBC53.099CCA10] | Benjamin Gould | 2026-03-25 12:32 | TRUE | 2026-03-27 13:20:20 - Jade Scherer (Work notes) [code]Issue:<br>A user reported that not all of their data on OneDrive was migrated, with some data successfully migrated and other parts missing, resulting in a hit-and-miss migration process.<br><br>Key Actions Taken:<br>&emsp;- Received the incident report from Greg Owens, a Cybersecurity SME, detailing the partial migration issue on OneDrive<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 1<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Impacted Services/CIs: N/A<br>&emsp;- Affected CIs: N/A​⁠⁠⁠​[/code] | 2026-03-27 13:20:20 - Jade Scherer (Work notes) [code]Issue:<br>A user reported that not all of their data on OneDrive was migrated, with some data successfully migrated and other parts missing, resulting in a hit-and-miss migration process.<br><br>Key Actions Taken:<br>&emsp;- Received the incident report from Greg Owens, a Cybersecurity SME, detailing the partial migration issue on OneDrive<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 1<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Impacted Services/CIs: N/A<br>&emsp;- Affected CIs: N/A​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-03-30 12:32 |  | GCC High Migration Support |  | INC0622634
INC0622575 | On Hold | Matthew.Sharpe@serco-na.com | In GCC High in Outlook, I am receiving meeting invitations from Serco colleagues in the .com domain. When I reply to those invitations, I get an error. See belo | In GCC High in Outlook, I am receiving meeting invitations from Serco colleagues in the .com domain. When I reply to those invitations, I get an error. See below. | Jade Scherer | 2026-03-25 09:47 | TRUE | 2026-04-02 16:18:28 - Jade Scherer (Work notes) Reaching out to Tracy West for support. 2026-03-31 13:43:11 - Benjamin Gould (Work notes) Not a mail / OneDrive migration related issue 2026-03-31 12:54:35 - William Alexander (Work notes) [code]Issue:<br>A user in GCC High is receiving meeting invitations from Serco colleagues in the .com domain and encountering an error when attempting to reply to these invitations. The user is unable to set the sensitivity label for the reply, and the issue may be related to restrictions when replying to external (commercial) emails.<br><br>Key Actions Taken:<br>&emsp;- Assigned the case to Benjamin Gould for further assistance<br>&emsp;- Advised the user to check the sensitivity label and set it to 'SB – NON CUI' for emails sent to Commercial users<br>&emsp;- Escalated the issue for deeper investigation due to lack of information on responses to external emails<br>&emsp;- Requested the user to verify the sensitivity label configuration when sending replies<br>​⁠⁠⁠​[/code] 2026-03-31 12:54:17 - William Alexander (Work notes) User is not able to change sensitivity label when replying to meeting invites being sent from .com email address to his GCCH email. Gets an error when trying to send the response normally (see screenshots). Assigning to Benjamin Gould for further assistance. 2026-03-27 14:39:52 - Jade Scherer (Work notes) Assigned to myself | 2026-04-02 16:18:28 - Jade Scherer (Work notes) Reaching out to Tracy West for support. 2026-03-31 13:43:11 - Benjamin Gould (Work notes) Not a mail / OneDrive migration related issue 2026-03-31 12:54:35 - William Alexander (Work notes) [code]Issue:<br>A user in GCC High is receiving meeting invitations from Serco colleagues in the .com domain and encountering an error when attempting to reply to these invitations. The user is unable to set the sensitivity label for the reply, and the issue may be related to restrictions when replying to external (commercial) emails.<br><br>Key Actions Taken:<br>&emsp;- Assigned the case to Benjamin Gould for further assistance<br>&emsp;- Advised the user to check the sensitivity label and set it to 'SB – NON CUI' for emails sent to Commercial users<br>&emsp;- Escalated the issue for deeper investigation due to lack of information on responses to external emails<br>&emsp;- Requested the user to verify the sensitivity label configuration when sending replies<br>​⁠⁠⁠​[/code] 2026-03-31 12:54:17 - William Alexander (Work notes) User is not able to change sensitivity label when replying to meeting invites being sent from .com email address to his GCCH email. Gets an error when trying to send the response normally (see screenshots). Assigning to Benjamin Gould for further assistance. 2026-03-27 14:39:52 - Jade Scherer (Work notes) Assigned to myself | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-03-30 09:47 |  | GCC High Migration Support |  | INC0622575
INC0622565 | Closed | William.Durant@serco-na.com | I need software installed on my GCCH laptop. The software is called SSI Tools and it is already paid for and installed on my commercial laptop. The software c | I need software installed on my GCCH laptop. The software is called SSI Tools and it is already paid for and installed on my commercial laptop. The software can be installed from the internet (the link is in the attached email) and then there are some configuration requirements to make the software work. The installation and configuration instructions are on the attached PDF. I have the product key 869f39bc-dfec-4c62-ac79-4b6c71a2245c | Jade Scherer | 2026-03-25 09:12 | FALSE | 2026-03-27 14:36:05 - Jade Scherer (Work notes) [code]Issue:<br>A user requires the SSI Tools software to be installed on their GCCH laptop, as it is already installed on their commercial laptop. The software is paid for, and installation instructions along with configuration requirements are provided in an attached PDF and email link. The user has provided the product key 869f39bc-dfec-4c62-ac79-4b6c71a2245c.​⁠⁠⁠​[/code] | 2026-03-27 14:36:05 - Jade Scherer (Work notes) [code]Issue:<br>A user requires the SSI Tools software to be installed on their GCCH laptop, as it is already installed on their commercial laptop. The software is paid for, and installation instructions along with configuration requirements are provided in an attached PDF and email link. The user has provided the product key 869f39bc-dfec-4c62-ac79-4b6c71a2245c.​⁠⁠⁠​[/code] | 0 | 373693 | 0 | 151200 | 0 | 2026-04-03 15:00 | FALSE | 2026-03-30 09:12 | 798493 | GCC High Migration Support |  | INC0622565
INC0622563 | Resolved | Clayton.Schaefer@serco-na.com | New laptop connects to my home wifi but does not show connected to internet. Connected via ethernet (and got internet access) when tried to connect to global p | New laptop connects to my home wifi but does not show connected to internet. Connected via ethernet (and got internet access) when tried to connect to global protect, it is not loaded on my laptop and it will not let me download it | John Hudson | 2026-03-25 09:10 | TRUE | 2026-03-25 10:04:24 - John Hudson (Work notes) Schaefer, Clayton, A (Serco NA US) 3/25/2026 9:41 AM After a number of re-starts, things are starting to come together. Please keep ticket open and follow up with me this afternoon, or i'll reach out if I hit another wall this morning. Thanks! 2026-03-25 09:29:48 - John Hudson (Work notes) [code]Issue:<br>A user reports that their new laptop connects to their home Wi-Fi but does not show as connected to the internet. When attempting to connect to Global Protect via Ethernet, the software is not loaded on the laptop, preventing download and access.​⁠⁠⁠​[/code] | 2026-03-25 10:04:24 - John Hudson (Work notes) Schaefer, Clayton, A (Serco NA US) 3/25/2026 9:41 AM After a number of re-starts, things are starting to come together. Please keep ticket open and follow up with me this afternoon, or i'll reach out if I hit another wall this morning. Thanks! 2026-03-25 09:29:48 - John Hudson (Work notes) [code]Issue:<br>A user reports that their new laptop connects to their home Wi-Fi but does not show as connected to the internet. When attempting to connect to Global Protect via Ethernet, the software is not loaded on the laptop, preventing download and access.​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-03-30 09:10 |  | GCC High Migration Support |  | INC0622563
INC0622501 | Closed | Deborah.Linton@serco-na.com | Confusing profile on my GCCH laptop | Serco Business Trying to follow the steps to set up my GCCH laptop, got this sent to my commercial email. Why was my old WBB profile even linked to this? Currently my laptop set up has failed. Debbie Linton Aero Engineer - System Architect, Serco-North America Office: 850.739.4873 ¦ Mobile: 301.247.0870 E-mail: deborah.linton@serco-na.com<mailto:deborah.linton@serco-na.com> NIPR: deborah.linton.ctr@us.af.mil<mailto:deborah.linton.ctr@us.af.mil> This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | William Alexander | 2026-03-24 18:50 | FALSE | 2026-03-26 14:07:47 - Jade Scherer (Work notes) @William Alexander Can you please get more details about what she means about her WBB profile and assist her with getting into her machine. | 2026-03-26 14:07:47 - Jade Scherer (Work notes) @William Alexander Can you please get more details about what she means about her WBB profile and assist her with getting into her machine. | 0 | 375002 | 0 | 151200 | 0 | 2026-04-03 11:00 | FALSE | 2026-03-27 18:50 | 835802 | GCC High Migration Support |  | INC0622501
INC0622477 | Resolved | guest | Commercial Emails Showing Up on GCC-H | Serco Business - Non CUI To Whom It May Concern - As part of the migration to GCC-H, I don't always see commercial emails showing up in the GCC-H inbox day-to-day Some do; some don't. Shouldn't they all make it over to GCC-H at some point? Or do I have to set up a rule to have commercial emails forwarded to GCC-H. There will be a period where people will think I am still on .com email when I have shifted to .us. So, they will email me at .com and those emails could get lost if they don't come to GCC-H on their own. Any insights into this? Thanks, Tim Winand Serco Agile Impact | Benjamin Gould | 2026-03-24 16:00 | TRUE | 2026-03-27 13:19:50 - Jade Scherer (Work notes) [code]Issue:<br>Commercial emails are inconsistently appearing in the GCC-H inbox after migration, causing potential loss of emails sent to the old .com address during the transition period.<br><br>Key Actions Taken:<br>&emsp;- A work note was added to assist the user with guidance on forwarding email<br>&emsp;- A comment was made indicating the cutover date for mail and calendar and noting that communication about forwarding commercial email to GCC-H should have been provided<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 2<br>&emsp;- Total number of breached SLAs: 1<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- In progress: 1<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: Priority 3 response (4 hours)<br>&emsp;&emsp;- Breach time: 24/03/2026 19:59:45<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Impacted Services/CIs: N/A<br>&emsp;- Affected CIs: N/A​⁠⁠⁠​[/code] 2026-03-26 15:09:31 - Benjamin Gould (Work notes) Please assist user with guidance on forwarding email 2026-03-26 14:07:31 - Jade Scherer (Work notes) [code]Issue:<br>Commercial emails are inconsistently appearing in the GCC-H inbox after migration, raising concerns about potential loss of emails sent to the old .com address during the transition period.<br><br>Key Actions Taken:<br>&emsp;- Received the incident report from Timothy Winand regarding missing commercial emails in the GCC-H inbox<br>&emsp;- Acknowledged the user's concern about emails sent to the old .com address during the migration transition period<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 1<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: N/A<br>&emsp;&emsp;- Breach time: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Impacted Services/CIs: N/A<br>&emsp;- Affected CIs: N/A​⁠⁠⁠​[/code] | 2026-03-27 13:19:50 - Jade Scherer (Work notes) [code]Issue:<br>Commercial emails are inconsistently appearing in the GCC-H inbox after migration, causing potential loss of emails sent to the old .com address during the transition period.<br><br>Key Actions Taken:<br>&emsp;- A work note was added to assist the user with guidance on forwarding email<br>&emsp;- A comment was made indicating the cutover date for mail and calendar and noting that communication about forwarding commercial email to GCC-H should have been provided<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 2<br>&emsp;- Total number of breached SLAs: 1<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- In progress: 1<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: Priority 3 response (4 hours)<br>&emsp;&emsp;- Breach time: 24/03/2026 19:59:45<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Impacted Services/CIs: N/A<br>&emsp;- Affected CIs: N/A​⁠⁠⁠​[/code] 2026-03-26 15:09:31 - Benjamin Gould (Work notes) Please assist user with guidance on forwarding email 2026-03-26 14:07:31 - Jade Scherer (Work notes) [code]Issue:<br>Commercial emails are inconsistently appearing in the GCC-H inbox after migration, raising concerns about potential loss of emails sent to the old .com address during the transition period.<br><br>Key Actions Taken:<br>&emsp;- Received the incident report from Timothy Winand regarding missing commercial emails in the GCC-H inbox<br>&emsp;- Acknowledged the user's concern about emails sent to the old .com address during the migration transition period<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 1<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: N/A<br>&emsp;&emsp;- Breach time: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Impacted Services/CIs: N/A<br>&emsp;- Affected CIs: N/A​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-03-27 16:00 |  | GCC High Migration Support |  | INC0622477
INC0622344 | Closed | Gary.Humes@serco-na.com | GCCH Migration | Serco Business I seem to have all my files transferred to my GCCH laptop but I don't have any of my Sharepoint groups or Teams chat. Is this because I have to access them only through my .com environment? If so, I don't know how to access my .com environment from my GCCH laptop, Also, on my GCCH laptop, I can't access any of the links (such as SercoConnect). I need some personal help. [A black background with grey letters and a red circle Description automatically generated] Gary Humes Sr. Naval SME Serco North America, Advanced Solutions Group (ASG) M: 1-202-570-0648 gary.humes@serco-na.us<mailto:gary.humes@serco-na.com> ¦ www.serco.com/na<http://www.serco.com/na> This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | Christopher Burns | 2026-03-24 10:15 | FALSE | 2026-03-25 11:02:54 - Jade Scherer (Work notes) [code]Issue:<br>A user reported that after transferring files to their GCCH laptop, they could not access Sharepoint groups, Teams chat, or links such as SercoConnect, and were unsure how to access their .com environment from the GCCH laptop.<br><br>Key Actions Taken:<br>&emsp;- Assigned the case to the user for distribution to their team<br>&emsp;- Included the user's contact information and company details in the case description<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 1<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Impacted Services/CIs: N/A<br>&emsp;- Affected CIs: N/A​⁠⁠⁠​[/code] 2026-03-24 11:14:29 - Jade Scherer (Work notes) @Amy Kimball Assigning to you for distribution to your team. | 2026-03-25 11:02:54 - Jade Scherer (Work notes) [code]Issue:<br>A user reported that after transferring files to their GCCH laptop, they could not access Sharepoint groups, Teams chat, or links such as SercoConnect, and were unsure how to access their .com environment from the GCCH laptop.<br><br>Key Actions Taken:<br>&emsp;- Assigned the case to the user for distribution to their team<br>&emsp;- Included the user's contact information and company details in the case description<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 1<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Impacted Services/CIs: N/A<br>&emsp;- Affected CIs: N/A​⁠⁠⁠​[/code] 2026-03-24 11:14:29 - Jade Scherer (Work notes) @Amy Kimball Assigning to you for distribution to your team. | 0 | 362703 | 0 | 151200 | 0 | 2026-04-02 13:00 | FALSE | 2026-03-27 10:15 | 787503 | GCC High Migration Support |  | INC0622344
INC0622342 | On Hold | Cassidy.Kuzemka@serco-na.com | The shared mailbox (avms-help@serco-na.com) didn't transfer over to my new gcch laptop. Those emails need to be transferred over. | The shared mailbox (avms-help@serco-na.com) didn't transfer over to my new gcch laptop. Those emails need to be transferred over. | Anthony Wilson | 2026-03-24 10:10 | TRUE | 2026-03-31 07:42:17 - Benjamin Gould (Work notes) I have no timetable for the migration of the requested shared mailbox 2026-03-25 11:46:27 - Jade Scherer (Work notes) [code]Issue:<br>The shared mailbox avms-help@serco-na.com did not transfer to a user's new gcch laptop, resulting in a need to transfer the emails.​⁠⁠⁠​[/code] | 2026-03-31 07:42:17 - Benjamin Gould (Work notes) I have no timetable for the migration of the requested shared mailbox 2026-03-25 11:46:27 - Jade Scherer (Work notes) [code]Issue:<br>The shared mailbox avms-help@serco-na.com did not transfer to a user's new gcch laptop, resulting in a need to transfer the emails.​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-03-27 10:10 |  | GCC High Migration Support |  | INC0622342
INC0622264 | On Hold | Scott.Adams@serco-na.com | Transfer files from old Serco laptop | I was issued a new ".com" laptop roughly 3-4 years ago. I was assigned an H: drive to migrate data from my old to new .com laptop. The "new" .com laptop is the one I currently have. Not all files were transferred from the H: drive to the new .com laptop; accordingly not all files have been transferred to my GCCH one drive. How can I ensure that all files on the H: drive will be transferred to the GCCH One drive? Thank you. |  | 2026-03-23 17:38 | TRUE | 2026-03-31 11:14:38 - Bradley Tucker (Work notes) User confirmed they are unable to migrate files normally as they do not have their old device any longer, and need files from this laptop on their new laptop. 2026-03-25 11:48:38 - Jade Scherer (Work notes) [code]Issue:<br>A user reported that not all files were transferred from the H: drive to their new .com laptop, which is the one they currently use, and subsequently not all files have been moved to their GCCH One Drive. The user seeks assistance to ensure all files on the H: drive are transferred to the GCCH One Drive.​⁠⁠⁠​[/code] | 2026-03-31 11:14:38 - Bradley Tucker (Work notes) User confirmed they are unable to migrate files normally as they do not have their old device any longer, and need files from this laptop on their new laptop. 2026-03-25 11:48:38 - Jade Scherer (Work notes) [code]Issue:<br>A user reported that not all files were transferred from the H: drive to their new .com laptop, which is the one they currently use, and subsequently not all files have been moved to their GCCH One Drive. The user seeks assistance to ensure all files on the H: drive are transferred to the GCCH One Drive.​⁠⁠⁠​[/code] | 47049 | 79837 | 31.12 | 104151 | 83049 |  | FALSE | 2026-03-26 17:38 | 151837 | GCC High Migration Support |  | INC0622264
INC0622240 | Closed | Brian.Hartless@serco-na.com | Pilot UAT Questions | Serco Business Good Afternoon, I received my GCCH laptop in the mail and was able to successfully log on to my new laptop per the instruction. I was able to open outlook and get my mail inbox set up. I have a few urgent questions and/or comments: 1. I was able to open outlook and my inbox looked okay, but none of my calendar items (reoccurring meetings, etc.) migrated to my new GCCH Microsoft outlook calendar. 1. TEAMS opened okay, but none of my TEAMS channels migrated and similar to my outlook calendar, none of my calendar items transitioned. 1. I urgently need to plan a trip in Concur. I was unable to open the Concur website in GCCH. Am I supposed to just plan this trip on my Serco commercial laptop? Thank you! Brian Brian Hartless Senior Civil Engineer, Serco Agile Impact Brian.Hartless@serco-na.com<mailto:Brian.Hartless@serco-na.com> M: 334-322-9644 Serco-North America, Inc This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | Benjamin Gould | 2026-03-23 15:52 | FALSE | 2026-03-25 11:51:57 - Jade Scherer (Work notes) [code]Issue:<br>A user reported issues with their new GCCH laptop, including missing calendar items in Outlook and Teams, and inability to access the Concur website, requiring clarification on using a Serco commercial laptop for travel planning.<br><br>Key Actions Taken:<br>&emsp;- Acknowledged the user's questions and concerns regarding M365 migration issues and Concur access.<br>&emsp;- Advised the user to use their Serco commercial laptop for Concur travel planning temporarily.<br>&emsp;- Escalated the M365-related questions to a team member for further investigation.<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 1<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: N/A<br>&emsp;&emsp;- Breach time: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Affected CIs: N/A<br>&emsp;- Impacted Services: N/A<br>&emsp;- Impacted Services/CIs: N/A​⁠⁠⁠​[/code] 2026-03-24 11:13:01 - Jade Scherer (Work notes) @Amy Kimball User has a question about M365. Wasn't sure how you wanted these distributed to your team. | 2026-03-25 11:51:57 - Jade Scherer (Work notes) [code]Issue:<br>A user reported issues with their new GCCH laptop, including missing calendar items in Outlook and Teams, and inability to access the Concur website, requiring clarification on using a Serco commercial laptop for travel planning.<br><br>Key Actions Taken:<br>&emsp;- Acknowledged the user's questions and concerns regarding M365 migration issues and Concur access.<br>&emsp;- Advised the user to use their Serco commercial laptop for Concur travel planning temporarily.<br>&emsp;- Escalated the M365-related questions to a team member for further investigation.<br><br>Service Level Agreement:<br>&emsp;- Total number of SLAs: 1<br>&emsp;- Total number of breached SLAs: 0<br>&emsp;- Number of SLAs by state:<br>&emsp;&emsp;- Paused: 1<br>&emsp;- Latest Breached SLA details:<br>&emsp;&emsp;- Name: N/A<br>&emsp;&emsp;- Breach time: N/A<br>&emsp;- Next SLA Breach details:<br>&emsp;&emsp;- Name: Priority 3 resolution (3 days)<br>&emsp;&emsp;- Time left: 1 Day 18 Hours<br><br>Affected CIs and Impacted Services:<br>&emsp;- Affected CIs: N/A<br>&emsp;- Impacted Services: N/A<br>&emsp;- Impacted Services/CIs: N/A​⁠⁠⁠​[/code] 2026-03-24 11:13:01 - Jade Scherer (Work notes) @Amy Kimball User has a question about M365. Wasn't sure how you wanted these distributed to your team. | 0 | 479265 | 0 | 151200 | 0 | 2026-04-06 09:00 | FALSE | 2026-03-26 15:52 | 1184865 | GCC High Migration Support |  | INC0622240
INC0622219 | Closed | Michael.Mcneill@serco-na.com | New GCCH laptop up and running, but something that hasn't transferred is Teams Channels from my old laptop to GCCH Teams channels. One of the most important Te | New GCCH laptop up and running, but something that hasn't transferred is Teams Channels from my old laptop to GCCH Teams channels. One of the most important Teams channels I need is Project Folders, Army market Team, it has the following channels: General, 22800 PMCCS CLS and 31689 IMAC. I support the IMAC customer and we are working on a proposal and it has over 10yrs of teaching files, student materials, updated materials and certification paperwork for the course being a DAU equivalent. Please let me know if these Teams channels will transfer to GCCH Teams or what i need to do. Thank you. Mike | Christopher Burns | 2026-03-23 15:06 | FALSE | 2026-03-25 15:26:49 - Jade Scherer (Work notes) [code]Issue:<br>A user reported that Teams channels from their old laptop, including Project Folders, Army market Team with channels General, 22800 PMCCS CLS, and 31689 IMAC, did not transfer to their new GCCH laptop. The user requires assistance to determine if these channels will transfer or what steps are needed to resolve the issue.​⁠⁠⁠​[/code] | 2026-03-25 15:26:49 - Jade Scherer (Work notes) [code]Issue:<br>A user reported that Teams channels from their old laptop, including Project Folders, Army market Team with channels General, 22800 PMCCS CLS, and 31689 IMAC, did not transfer to their new GCCH laptop. The user requires assistance to determine if these channels will transfer or what steps are needed to resolve the issue.​⁠⁠⁠​[/code] | 0 | 395659 | 0 | 151200 | 0 | 2026-04-02 13:00 | FALSE | 2026-03-26 15:06 | 856459 | GCC High Migration Support |  | INC0622219
INC0622198 | Closed | Christopher.Pritchet@serco-na.com | GCC High Wi-Fi Connection Problem | Serco Business At the point in the laptop instructions where I connect my new laptop to the internet through Wi-Fi, I am only able to connect to gSAM. Dominic Litwin told me this morning that iSAM and cSAM are only for hard wire connection. That cannot be since I do not have a working ethernet/hard wire wall outlet in my Serco office. I have been on cSAM for 5+ years. If all I can connect to is gSAM, I will have to have a new guest password every 30 days??? C. Scott Pritchett Sr. Operations Analyst Serco-NA Tel: (757) 350-4395 Serco: christopher.pritchet@serco-na.com<mailto:christopher.pritchet@serco-na.com> Serco CUI: christopher.pritchet@serco-na.us<mailto:christopher.pritchet@serco-na.us> NIPRNet: christopher.pritchett.3.ctr@us.af.mil<mailto:christopher.pritchett.3.ctr@us.af.mil> SIPRNet: christopher.pritchett7.ctr@mail.smil.mil<mailto:christopher.pritchett7.ctr@mail.smil.mil> This e-mail and any attachments are for the intended recipient(s) only and may contain proprietary, sensitive, and/or privileged information. If you are not the intended recipient, (even if the email address above is yours) do not use, retain, copy or disclose any part of this communication or any attachment as it is strictly prohibited and may be unlawful. If you believe that you have received this e-mail in error, please notify the sender immediately and permanently delete. This email may be a personal communication from the sender and as such does not represent the views of the company. Thank you. | Jade Scherer | 2026-03-23 13:54 | FALSE |  |  | 0 | 403602 | 0 | 151200 | 0 | 2026-04-02 14:00 | FALSE | 2026-03-26 13:54 | 864402 | GCC High Migration Support |  | INC0622198
INC0622194 | Closed | Matthew.Sharpe@serco-na.com | My Outlook calendar items did not migrate. | My Outlook calendar items did not migrate. | Benjamin Gould | 2026-03-23 13:49 | FALSE |  |  | 0 | 490266 | 0 | 151200 | 0 | 2026-04-06 10:00 | FALSE | 2026-03-26 13:49 | 1195866 | GCC High Migration Support |  | INC0622194
INC0622193 | In Progress | Matthew.Sharpe@serco-na.com | My SharePoint/Teams/M365 groups (10 owned, 133 member), chats, and calendar items did not migrate. | My SharePoint/Teams/M365 groups (10 owned, 133 member), chats, and calendar items did not migrate. | Christopher Burns | 2026-03-23 13:48 | TRUE | 2026-04-03 11:35:04 - Jade Scherer (Work notes) @Christopher Burns Can you please follow up with the user to see if this is resolved? 2026-03-25 15:26:17 - Jade Scherer (Work notes) [code]Issue:<br>A user reported that 10 owned and 133 member SharePoint/Teams/M365 groups, along with chats and calendar items, did not migrate. The user also noted that their teams were not listed in the Migration Registry and emphasized the need for access to Teams to function in a GCC High environment.​⁠⁠⁠​[/code] | 2026-04-03 11:35:04 - Jade Scherer (Work notes) @Christopher Burns Can you please follow up with the user to see if this is resolved? 2026-03-25 15:26:17 - Jade Scherer (Work notes) [code]Issue:<br>A user reported that 10 owned and 133 member SharePoint/Teams/M365 groups, along with chats and calendar items, did not migrate. The user also noted that their teams were not listed in the Migration Registry and emphasized the need for access to Teams to function in a GCC High environment.​⁠⁠⁠​[/code] | 0 |  | 0 | 151200 | 0 |  | FALSE | 2026-03-26 13:48 |  | GCC High Migration Support |  | INC0622193
INC0622185 | Closed | Matthew.Sharpe@serco-na.com | In my .com environment, I have files archived in an H: drive at \\snaclfs01\homedir. How can I access this drive from the .us laptop? | In my .com environment, I have files archived in an H: drive at \\snaclfs01\homedir. How can I access this drive from the .us laptop? | Jade Scherer | 2026-03-23 13:09 | FALSE |  |  | 0 | 363051 | 0 | 151200 | 0 | 2026-04-01 16:00 | FALSE | 2026-03-26 13:09 | 787851 | GCC High Migration Support |  | INC0622185
INC0622181 | Closed | Matthew.Sharpe@serco-na.com | I currently use the following apps on my .com laptop. How do I load them onto my .us laptop?Power BI Desktop, Python, Visio, Visual Studio, Visual Studio Cod | I currently use the following apps on my .com laptop. How do I load them onto my .us laptop? Power BI Desktop, Python, Visio, Visual Studio, Visual Studio Code? |  | 2026-03-23 13:05 | FALSE | 2026-03-26 12:14:04 - Oleksandra Larina Haleblian (Work notes) please resync your company portal and you will see all of this software available for install. https://sercona.service-now.com/esc?id=kb_article&sysparm_article=KB0011488 2026-03-26 10:55:32 - Oleksandra Larina Haleblian (Work notes) all software requirement have been submitted by your Business Champions. Project team is working on giving you access to the requested software. you will have it available in Company portal by 3/30 | 2026-03-26 12:14:04 - Oleksandra Larina Haleblian (Work notes) please resync your company portal and you will see all of this software available for install. https://sercona.service-now.com/esc?id=kb_article&sysparm_article=KB0011488 2026-03-26 10:55:32 - Oleksandra Larina Haleblian (Work notes) all software requirement have been submitted by your Business Champions. Project team is working on giving you access to the requested software. you will have it available in Company portal by 3/30 | 0 | 402952 | 0 | 151200 | 0 | 2026-04-02 13:00 | FALSE | 2026-03-26 13:05 | 863752 | GCC High Migration Support |  | INC0622181
INC0622127 | Closed | Anthony.Wilson@serco-na.com | Please make sure Amy.Kimball@serco-na.com has access to ServiceNow. If fixed please resolve | Please make sure Amy.Kimball@serco-na.com has access to ServiceNow. If fixed please resolve | Anthony Wilson | 2026-03-23 11:27 | FALSE | 2026-03-25 18:06:17 - Anthony Wilson (Work notes) This is a TEST of TESTS | 2026-03-25 18:06:17 - Anthony Wilson (Work notes) This is a TEST of TESTS | 0 | 131755 | 0 | 151200 | 0 | 2026-03-25 20:03 | FALSE | 2026-03-26 11:27 | 203755 | GCC High Migration Support |  | INC0622127
INC0621786 | Closed | Shaun.Aubain@serco-na.com | Tom reached out unable to connect to the wireless on his GCCH laptop at the Hampton location | Tom reached out unable to connect to the wireless on his GCCH laptop at the Hampton location | Shaun Aubain | 2026-03-19 15:35 | FALSE |  |  | 0 | 253506 | 0 | 151200 | 0 | 2026-03-26 16:00 | FALSE | 2026-03-24 15:35 | 606306 | GCC High Migration Support |  | INC0621786